## Sheet1
No. | Date | People | Content
1 | 2018-06-21 | Thao | - Test SKU:SEN0186 sensor kit: SKU:SEN0186 seem to work fine - Test sensor temperature & humidity AM2320: AM2320 has been broken and not return any data. So, i decided to buy SHT10 for replacing - Implement a library that used for parsing weather data string received from STC15
2 | 2018-06-21 | Hao | - Code demo neural network ( calculator XOR) and complete document of neural network
3 | 2018-06-22 | Thao | - Burn Arduino bootloader & soldering Atmega328p on Node - Setup Raspberry Pi: install MongoDB (old version, version > 3.0 not supported for Arm architeture) - Write Code that collect weather data on Raspberry. Still has some issues, cause MongoDB & MongoDB driver is not fully supported on ARM architeture.
4 | 2018-06-25 | Thao | - Update source code collected data on Raspberry to save to text file instead of saving to MongoDB
5 | 2018-06-26 | Hao | - Code demo multi layer neural network ( Complete ) - Design model neural for KLTN ( not complete)
6 | 2018-07-07 | Thao | -Build LoRa board for gateway - MongoDB Socket Driver for Server
7
8
9
10
11
12
13
14
15
16
17
18
19
20